## Sheet1
Day | Date | Task | Owner | Dependencies | Requirements | Deliverable/Goal
1 | 2025-09-08 | Kickoff call with estate attorney to outline trust and FLP setup | You + Estate Attorney |  | Attorney engagement letter; availability for kickoff call | Clear roadmap for trust and FLP drafting
2 | 2025-09-09 | Attorney drafts irrevocable trust document with dynasty provisions | Estate Attorney | Day 1 kickoff call | Attorney notes; jurisdiction decision (NV, SD, etc.) | First draft of irrevocable trust prepared
3 | 2025-09-10 | Review trust draft and provide comments | You | Day 2 draft prepared | Draft trust document from attorney | Feedback returned to attorney
4 | 2025-09-11 | Attorney incorporates feedback and finalizes trust | Estate Attorney | Day 3 feedback provided | Reviewed draft with comments | Irrevocable trust finalized and ready for execution
5 | 2025-09-12 | Execute irrevocable trust; notarization and witness signatures | You + Attorney | Day 4 finalized trust document | Notary, witnesses, final trust document | Trust officially executed and legally valid
6 | 2025-09-13 | Attorney drafts Family Limited Partnership (FLP) agreement | Estate Attorney | Day 1 kickoff call | Outline of partners, ownership splits, GP/LP roles | Draft FLP agreement prepared
7 | 2025-09-14 | Review FLP agreement draft | You | Day 6 draft FLP agreement | Draft FLP agreement from attorney | Feedback returned to attorney
8 | 2025-09-15 | Attorney incorporates feedback and finalizes FLP agreement | Estate Attorney | Day 7 feedback provided | Reviewed draft with comments | Final FLP agreement ready for execution
9 | 2025-09-16 | Execute FLP agreement with partners; notarization | You + Attorney + Partners | Day 8 final FLP agreement | Partners present, notary, final FLP agreement | FLP legally executed
10 | 2025-09-17 | Form Parent Holding Company LLC (WY/DE) | Corporate Attorney / Filing Service | Day 5 trust executed | Articles of Organization, registered agent service | HoldCo LLC legally formed
11 | 2025-09-18 | Apply for EIN for Parent HoldCo and Trust | You / CPA | Day 10 HoldCo formed | IRS Form SS-4, trust executed documents | EINs obtained for HoldCo and Trust
12 | 2025-09-19 | Form Management Company LLC (elect S-Corp status) | Corporate Attorney / CPA | Day 10 HoldCo formed | Articles of Organization, registered agent, Form 2553 | MgmtCo legally formed and S-Corp election filed
13 | 2025-09-20 | Open bank accounts for Trust, FLP, HoldCo, and MgmtCo | You / Bank Officer | Day 5 trust executed, Day 9 FLP executed, Day 10 HoldCo formed | Entity documents, EINs, resolutions | Bank accounts opened for each entity
14 | 2025-09-21 | Form Real Estate Holding LLC and Asset Holding LLC | Corporate Attorney / Filing Service | Day 10 HoldCo formed | Articles of Organization, registered agent service | REI LLC and AssetCo legally formed
15 | 2025-09-22 | Kickoff compliance calendar setup and document repository | You / CPA / Attorney | All prior entity formations completed | Compliance calendar template, cloud storage setup | Compliance framework initiated