## Sheet1
Task | Start | End | Description | Dependencies
Phase 1: Entity & Trust Formation | 2025-09-08 | 2025-09-23 | Engage attorneys, draft irrevocable trust and FLP, form holding company, management company, real estate holding entities, and open bank accounts.
Phase 2: Ownership Assignments & Asset Transfers | 2025-09-23 | 2025-10-08 | Assign FLP and trust ownership, transfer IP and equipment, execute IP licenses and equipment leases. | Phase 1: Entity & Trust Formation
Phase 3: Intercompany Agreements & Chart of Accounts | 2025-10-08 | 2025-10-23 | Execute MSAs, cost-sharing, and intercompany loan agreements; update chart of accounts and accounting systems. | Phase 2: Ownership Assignments & Asset Transfers
Phase 4: Retirement & Philanthropy Setup | 2025-10-23 | 2025-11-07 | Fund Solo 401(k), set up plan-owned LLC, ILIT policy, file Form 1023, adopt nonprofit bylaws, seed initial contributions. | Phase 3: Intercompany Agreements & Chart of Accounts
Phase 5: Governance Review & Compliance Calendar | 2025-11-07 | 2025-12-07 | Adopt operating agreements, elect managers, approve transfer pricing policies, establish compliance calendar. | Phase 4: Retirement & Philanthropy Setup
Phase 6: SuiteDash Onboarding & Data Migration | 2025-12-08 | 2025-12-27 | Conduct due diligence, plan and execute data migration, set up portals, RACI roles, automations, and project templates. | Phase 5: Governance Review & Compliance Calendar
Phase 7: Neat Circle Service Package Integration | 2025-12-28 | 2026-01-16 | Implement Neat Circle service packages for customer support, marketing, business systems, and growth systems. | Phase 6: SuiteDash Onboarding & Data Migration
Phase 8: Launch ToriMedia Campaigns | 2026-01-17 | 2026-02-05 | Create brand assets, content calendars, influencer and paid media campaigns; link metrics back to SuiteDash. | Phase 7: Neat Circle Service Package Integration
Phase 9: Harmonise Operations & Pricing | 2026-02-06 | 2026-03-07 | Standardise service offerings and pricing, finalise leasebacks, train staff using SuiteDash guides, adjust projections. | Phase 8: Launch ToriMedia Campaigns
Phase 10: Scale & Governance | 2026-03-08 | 2026-09-08 | Acquire two businesses per quarter, onboard them into SuiteDash, deploy Neat Circle and ToriMedia, establish quarterly board meetings. | Phase 9: Harmonise Operations & Pricing