## Lead_to_Client
Seq # (Chrono) | Phase | Sub-Process | Step Name | Detailed Instructions (Novice) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | SLA Target (Response/Resolution/Due) | Inputs / Forms / Data | Outputs / Artifacts | SuiteDash Module / Feature | Automation Trigger (if any) | Automated Actions | Manual Actions | Dependencies (Predecessors) | Definition of Done (Checklist) | QA Gate / Approval | Exception Handling | Escalation Path | Metrics / KPI | Evidence Log / Where | Security / Data Class | Tools / Integrations | Template ID / Link (placeholder) | Owner (Role) | Version / Last Updated
1 | Lead → Client (Funnel & Sales) | Attract | Publish Lead Magnet Landing Page | Create a simple landing page (headline = dream outcome + fast time, 1 CTA). Embed SuiteDash public form OR website form connected via Zapier/Activepieces to SuiteDash CRM. | Marketing Manager | Marketing Manager | IT/Security; Ops Manager | CEO | Go-live by EOD; uptime 99.9% | Lead Magnet PDF/Video; Opt-in Form | Public URL; Form endpoint | Portal Pages (Public) / Forms | N/A | N/A | Write copy, add form, test submission | None | • Page loads • Test opt-in submits to CRM • Thank-you page functions | Ops review of copy & opt-in | If page errors → revert to backup page | Notify Ops via Slack/email | Opt-in rate %, Page load time | Website change log; Form submissions | Public/Marketing (no PII until submit) | Zapier/Activepieces, CMS | TPL-LP-001 | Marketing Manager | v1.0 / 2025-09-06 22:10
2 | Lead → Client (Funnel & Sales) | Capture | Configure SuiteDash Lead Capture Form | In SuiteDash: Forms → Create 'Lead Magnet Opt-in'. Add fields: First Name, Last Name, Email, Consent checkbox. Map to CRM fields. Enable double opt-in if required. | Marketing Manager | Ops Manager | Legal/Compliance | CEO | Form live within 24h | Form builder; Field list | Form ID, CRM field mapping | Forms → CRM mapping | Form Submitted | Auto-create Contact; Tag = 'LeadMagnet_X' | QA test submission with test email | 1 | • Contact auto-created • Tag applied • Confirmation email sent | Ops to sign-off mapping | If duplicate email → update existing, append tag | Create 'Data Merge' task to CSM | Contacts created, Duplicate rate | SuiteDash Audit Log | PII (Email) | Zapier/Activepieces | FORM-LEAD-001 | Ops Manager | v1.0 / 2025-09-06 22:10
3 | Lead → Client (Funnel & Sales) | Nurture | Start Soap Opera Email Sequence (5 emails) | Load 5-email onboarding (SOS) sequence in SuiteDash Email Campaigns. Personalize with merge fields. Schedule Day0..Day4. Include CTA to book call (Calendly). | Marketing Manager | Marketing Manager | Sales Manager | CEO | Email #1 within 5 minutes of opt-in | Email templates; List Segment 'LeadMagnet_X' | Queued campaign | Email Marketing / Campaigns | Contact Tagged = LeadMagnet_X | Send Email 1..5 on schedule | Review copy, test links, enable | 2 | • Emails sent on time • Links tracked • Unsub link present | Legal review for compliance | If bounce/spam complaints ↑ → pause & edit copy | Notify Marketing Lead; switch to plain-text variant | Open %, CTR, Call bookings | Email logs; UTM tracking | PII | Calendly, GA4, UTM | EML-SOS-001..005 | Marketing Manager | v1.0 / 2025-09-06 22:10
4 | Lead → Client (Funnel & Sales) | Qualify | Score Leads & Route to SDR | Create simple lead score: +5 opened Email#3, +10 clicked CTA, +20 booked call. If score ≥ 20 → assign SDR; else remain in nurture. | Sales Ops | Sales Manager | Marketing Manager | CEO | Scoring runs hourly | Engagement events | Assigned Owner; Priority field | CRM Automations | Email Click / Calendly Booking | Auto-assign Owner=SDR; create 'Discovery Call' task | Review assigned leads daily | 3 | • Owner assigned • Task created • SLA timer started | Sales Manager approval on rules | If misrouted → reassign within 2h | Escalate to Sales Manager | MQL→SQL rate, Time-to-first-touch | CRM activity log | PII | Calendly, GA4 | AUTO-SCORE-001 | Sales Ops | v1.0 / 2025-09-06 22:10
5 | Lead → Client (Funnel & Sales) | Sell | Discovery Call & Proposal | SDR performs 15-min discovery using script. If fit → AE sends Proposal via SuiteDash Proposals (with e-sign + Stripe link). | SDR / AE | Sales Manager | Ops Manager (pricing) | CEO | Respond (booked) ≤ 24h; Proposal ≤ 24h post-call | Discovery script; Proposal template; Pricing sheet | Call notes; Signed proposal | Proposals & eSigning; Invoices/Subscriptions | Deal Stage = Qualified | On sign: auto-create Onboarding Project; send Welcome email | Conduct call, prepare proposal | 4 | • Proposal sent • Client understands scope • Follow-up scheduled | Manager reviews discount >10% | If no response in 3 days → reminder email | Escalate to Sales Manager at 7 days | Close rate, Cycle time | Proposal logs; eSign audit | PII + Contract | Stripe/PayPal | PROP-BOS-CORE | Account Executive | v1.0 / 2025-09-06 22:10

## Onboarding
Seq # (Chrono) | Phase | Sub-Process | Step Name | Detailed Instructions (Novice) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | SLA Target (Response/Resolution/Due) | Inputs / Forms / Data | Outputs / Artifacts | SuiteDash Module / Feature | Automation Trigger (if any) | Automated Actions | Manual Actions | Dependencies (Predecessors) | Definition of Done (Checklist) | QA Gate / Approval | Exception Handling | Escalation Path | Metrics / KPI | Evidence Log / Where | Security / Data Class | Tools / Integrations | Template ID / Link (placeholder) | Owner (Role) | Version / Last Updated
1 | Client Onboarding | Kickoff | Auto-Provision Client & Portal | Upon e-sign/payment, SuiteDash automation creates Contact/Company, assigns Circles, and enables Portal access. Verify client can log in. | Ops Admin | Ops Manager | IT/Security | CEO | Within 1 hour of signature | Signed proposal; Payment event | Active client record; Portal access | CRM / Portal Access | Proposal Signed / Invoice Paid | Create Contact/Company; Assign Group; Email credentials | Login test with client | Lead→Client:5 | • Contact exists • Portal active • Client confirmed login | Ops approval | If login fails → reset & resend invitation | Escalate to IT at +2h | Time-to-portal (TTP) | Activity log; Email confirmation | PII | Stripe webhook, Email | AUTO-ONB-001 | Ops Admin | v1.0 / 2025-09-06 22:10
2 | Client Onboarding | Kickoff | Send Welcome Email & Start Onboarding FLOW | Use template 'Welcome + Next Steps' including: intro, portal URL, support hours, link to Kickoff Form, and Calendly link for Kickoff call. | CSM | Ops Manager | Sales (handoff) | CEO | Send ≤ 2h after signature | Email template; Links; Onboarding FLOW ID | Sent email; FLOW started | Email Campaigns; FLOWs | Client added to Circle 'New' | Queue FLOW steps: Form → Contract → Booking | Personalize greeting; send | 1 | • Email delivered • FLOW visible in client portal | QA by PM (first 5 clients) | If bounce → verify email; call client | Notify Ops Manager | Welcome open rate; FLOW start rate | Email log; FLOW history | PII | Calendly | EML-WELCOME-001 | CSM | v1.0 / 2025-09-06 22:10
3 | Client Onboarding | Data Intake | Kickoff Form Completion | Client completes Kickoff Form (company details, goals, assets, access, compliance). Validate required fields; auto-map to CRM. | Client / CSM (assist) | CSM Lead | Legal/Compliance | Ops Manager | Form complete ≤ 3 days | Kickoff Form (see Form Schema workbook) | CRM fields populated; Attachments stored | Forms → CRM Mapping; Files | Form Submitted | Update CRM; Create checklist tasks | Review submissions; request missing items | 2 | • All required fields present • Attachments virus-scanned • CRM updated | CSM review sign-off | If missing req. fields → auto-reminder at +48h | Escalate to CSM Lead at +96h | Intake completion %, Days-to-complete | Form submissions; Files | PII / Confidential | Virus scan / DLP (if used) | FORM-KICKOFF-001 | CSM | v1.0 / 2025-09-06 22:10
4 | Client Onboarding | Planning | Kickoff Call | Conduct 45–60 min Zoom/Meet: confirm goals, timelines, success metrics, constraints. Record notes in CRM custom fields. Agree on next steps. | CSM / PM | PM | Sales AE | Client Exec | Schedule ≤ 5 business days; summary sent ≤ 24h | Agenda template; Calendly event | Call recording; Meeting notes; Updated plan | Calendar; CRM Notes; Projects | Event Scheduled | Create/Update Project from template | Host call; save notes; set expectations | 3 | • Success metrics captured • Risks logged • Next tasks assigned | PM approves plan | If no-show → reschedule once; if 2nd no-show → pause project | Escalate to Ops Manager | Kickoff scheduled rate; NPS post-call | CRM notes; Project activity | PII / Confidential | Zoom/Meet | TPL-AGENDA-ONB | PM | v1.0 / 2025-09-06 22:10
5 | Client Onboarding | Setup | Create Project from Template | Use 'BOS Onboarding' project template: auto-create task lists (branding, access, config). Assign owners & due dates. | PM | PM | Ops Admin | CSM Lead | Project within 24h post-call | Template TPL-PROJ-ONB | Active Project with tasks | Projects / Templates | PM clicks 'Create from Template' | Create tasks; assign to roles; due dates set | Adjust task dates to client timezone | 4 | • Tasks assigned • Start & due dates set • Dependencies mapped | Peer review by another PM | If capacity >85% → reassign tasks | Escalate to Ops Manager | On-time task start %, WIP | Project logs | Internal | None | TPL-PROJ-ONB | PM | v1.0 / 2025-09-06 22:10
6 | Client Onboarding | Access | Provision Integrations & Credentials | Collect required access (e.g., website, DNS, email). Store securely. Test connectivity. Document in Credentials vault. | IT/Security | IT/Security | PM | Ops Manager | Access verified ≤ 3 days from request | Access Request checklist; Client-provided creds | Validated access; Secrets stored | Files / Password Vault (if applicable) | Credential item added | Notify PM on success/failure | Test login; record method; enable 2FA | 5 | • Credentials validated • MFA enabled where possible | Security review | If access denied → re-request with guidance | Escalate to PM at +48h | Access cycle time; Fail rate | Access log | Confidential | Password manager (internal) | CHK-ACCESS-ONB | IT/Security | v1.0 / 2025-09-06 22:10
7 | Client Onboarding | Comms | Portal Orientation for Client | Publish a short Loom/Video: how to use portal (where to see tasks, files, invoices). Add to client portal page. | CSM | CSM Lead | PM | Client | Video shared ≤ 24h after project start | Orientation script; Video link | Portal page updated | Portal Pages / LMS | N/A | N/A | Record video; embed link; notify client | 5 | • Video visible in portal • Client confirms view | PM acknowledgment | If client confused → schedule 15-min walkthrough | Escalate to CSM Lead | Portal adoption %, Views | Portal page analytics | Public/Internal | Loom/Vimeo | PAGE-ORIENT-001 | CSM | v1.0 / 2025-09-06 22:10

## Delivery_Monthly
Seq # (Chrono) | Phase | Sub-Process | Step Name | Detailed Instructions (Novice) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | SLA Target (Response/Resolution/Due) | Inputs / Forms / Data | Outputs / Artifacts | SuiteDash Module / Feature | Automation Trigger (if any) | Automated Actions | Manual Actions | Dependencies (Predecessors) | Definition of Done (Checklist) | QA Gate / Approval | Exception Handling | Escalation Path | Metrics / KPI | Evidence Log / Where | Security / Data Class | Tools / Integrations | Template ID / Link (placeholder) | Owner (Role) | Version / Last Updated
1 | Service Delivery (Recurring) | Cycle Start | Clone Monthly Task Set | On day 1 each month, clone 'Monthly Delivery' task list into the client project. Set due dates (use relative offsets). | PM | PM | Ops Admin | CSM | Tasks live by Day 1 10:00 | Task template TPL-DELIV-MONTH | Task instances in project | Projects / Templates | Monthly schedule | Auto-clone task list | Verify dates & assignees | Onboarding:5 | • All tasks present • Owners assigned • Dependencies correct | Peer PM checklist | If resource conflict → move dates or reassign | Escalate to Ops | On-time starts | Project log | Internal | None | TPL-DELIV-MONTH | PM | v1.0 / 2025-09-06 22:10
2 | Service Delivery (Recurring) | Work | Execute Tasks & Time Tracking | Each assignee executes tasks and logs time (billable vs non-billable). Attach deliverables to tasks. | Task Owners | PM | CSM | Ops Manager | Time log within same day of work | Task checklist; Time tracking guidance | Completed tasks; Time entries | Tasks; Time Tracking | Task status change | Notify PM on completion | Do work; upload files; mark done | 1 | • Task marked done • Time logged • Files attached | PM spot-check | If late >24h → auto-reminder to assignee | Escalate to PM at +48h | Task on-time %, Utilization %, Margin | Time log; Files | Internal/Client | None | CHK-EXEC-001 | Task Owners | v1.0 / 2025-09-06 22:10
3 | Service Delivery (Recurring) | Review | Internal QA & Peer Review | Before client delivery, peer reviews deliverables using DoD checklist (spelling, links, data accuracy, brand). | QA Reviewer | PM | CSM | Ops Manager | QA within 24h of task completion | DoD checklist; Brand guide | QA-approved deliverable | Tasks; Files | Task moved to 'Ready for QA' | Notify assigned reviewer | Run checklist; comment fixes | 2 | • All DoD items checked • Reviewer approval recorded | PM final sign-off | If major issues → re-open task | Escalate chronic issues to Ops | Rework rate; QA defects | Task comments | Internal | None | DOD-DELIV-001 | QA Reviewer | v1.0 / 2025-09-06 22:10
4 | Service Delivery (Recurring) | Comms | Client Update & Deliverables | Send client a consolidated update via Portal message/email: what was done, results, next steps. Attach deliverables. | CSM | CSM Lead | PM | Client Exec | Monthly update by Day 5 | Update template; Deliverables | Message sent; Client acknowledged | Messages/Chat; Files | Task list completed | N/A | Write update; send; log | 3 | • Client confirms receipt • Follow-up actions noted | PM review first 2 cycles | If client unresponsive 3d → reminder | Escalate to CSM Lead | Client satisfaction; Response time | Message log | Client | Email | EML-UPDATE-001 | CSM | v1.0 / 2025-09-06 22:10
5 | Service Delivery (Recurring) | Reporting | Monthly KPI Report & Review | Generate KPI report (dashboards or PDF). Review with client in 30-min call. Capture action items. | Analyst / CSM | PM | Client | Ops Manager | Report by Day 7; Call by Day 10 | KPI tree; Data sources | Report file; Meeting notes | Dashboards; Files; Calendar | End-of-month | N/A | Compile data; create report; schedule call | 4 | • KPIs updated • Client agreed actions logged | PM approves before sharing | If data gaps → add tasks to fix instrumentation | Escalate to Ops | Target vs Actual; Churn risk | Dashboard links; Notes | Client/Internal | GA4/Stripe/etc. | RPT-KPI-001 | Analyst | v1.0 / 2025-09-06 22:10

## Support_Escalation
Seq # (Chrono) | Phase | Sub-Process | Step Name | Detailed Instructions (Novice) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | SLA Target (Response/Resolution/Due) | Inputs / Forms / Data | Outputs / Artifacts | SuiteDash Module / Feature | Automation Trigger (if any) | Automated Actions | Manual Actions | Dependencies (Predecessors) | Definition of Done (Checklist) | QA Gate / Approval | Exception Handling | Escalation Path | Metrics / KPI | Evidence Log / Where | Security / Data Class | Tools / Integrations | Template ID / Link (placeholder) | Owner (Role) | Version / Last Updated
1 | Support & Escalation | Intake | Ticket Submission (Portal/Email) | Client opens a ticket via portal or support@ email. Categorize (How-to, Incident, Billing). Auto-assign priority. | Client / L1 Support | Support Lead | CSM | PM | Response: P1 1h, P2 4h, P3 1 bus. day | Ticket form/email | Ticket with ID; Category; Priority | Support Tickets | Ticket Created | Auto-acknowledge; SLA timer start | L1 triage within SLA | N/A | • Acknowledged • Category set • Owner assigned | Support Lead audit | If miscategorized → recategorize | Escalate P1 immediately to L2 | SLA met %, First response time | Ticket log | Client/PII | Email, Slack (alerts) | TPL-TKT-INTAKE | Support Lead | v1.0 / 2025-09-06 22:10
2 | Support & Escalation | Resolution | L1 Troubleshoot or Route | Follow KB/SOP to resolve. If blocked >30m or P1, escalate to L2. Document steps taken. | L1 Support | Support Lead | IT/Security | CSM | Resolution: P1 4h; P2 8h; P3 3d | KB articles; SOP runbooks | Resolution comment; Status updated | Support Tickets; Knowledge Base | Ticket updated | Notify client on progress | Apply fix; test; update status | 1 | • Client confirms fix • Root cause noted (if incident) | Support Lead spot-check | If recurring issue → open problem record | Escalate to Ops for RCA | Resolution time; Reopen rate | Ticket history | Client/PII | Status page (if any) | RUNBOOK-INC-001 | L1 Support | v1.0 / 2025-09-06 22:10

## Offboarding
Seq # (Chrono) | Phase | Sub-Process | Step Name | Detailed Instructions (Novice) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | SLA Target (Response/Resolution/Due) | Inputs / Forms / Data | Outputs / Artifacts | SuiteDash Module / Feature | Automation Trigger (if any) | Automated Actions | Manual Actions | Dependencies (Predecessors) | Definition of Done (Checklist) | QA Gate / Approval | Exception Handling | Escalation Path | Metrics / KPI | Evidence Log / Where | Security / Data Class | Tools / Integrations | Template ID / Link (placeholder) | Owner (Role) | Version / Last Updated
1 | Offboarding | Notice | Receive Cancellation / Non-Renewal | Capture request via portal/email. Confirm effective date. Trigger offboarding project template. | CSM | CSM Lead | Finance | PM | Acknowledge ≤ 1 business day | Client request | Offboarding project created | Projects / Templates | Tag = Cancelled OR Sub ends | Create offboarding tasks; notify finance | Confirm date; set tasks | N/A | • Confirmation sent • Project started | PM approval | If save opportunity → offer downgrade/pause | Escalate to Sales for save | Save rate; Time to closure | Project log | Client | Stripe/Subscriptions | TPL-OFFB-001 | CSM | v1.0 / 2025-09-06 22:10
2 | Offboarding | Data | Export & Deliver Client Data | Export all client-owned data (reports, files). Provide secure download link with expiry. Log delivery. | Ops Admin | Ops Manager | IT/Security | Client | Data ready ≤ 7 days from request | Data export SOP | Zip file + checksum; Delivery receipt | Files / Secure link | Offboarding project task | Notify client with link | Collect & package; virus-scan; deliver | 1 | • Client confirms receipt • Hash matches | Security review | If too large → split packages | Escalate to IT | Delivery time; Data completeness | Delivery log | Confidential | Secure file share | EXP-DATA-001 | Ops Admin | v1.0 / 2025-09-06 22:10
3 | Offboarding | Access | Revoke Access & Remove PII | Disable portal access. Remove user/group permissions. Delete or anonymize PII per retention policy. | IT/Security | IT/Security | Legal/Compliance | Ops Manager | Within 2 business days post-termination | User list; Retention policy | Access revoked; PII removed/anonymized | Portal Access; CRM | Cancellation effective | N/A | Update roles/groups; run deletion jobs | 2 | • Access removed • Deletion log stored | Compliance approval | If legal hold → postpone deletion | Escalate to Legal | Access revocation SLA; Audit pass | Audit log; Deletion report | Confidential/PII | None | POL-RET-PII | IT/Security | v1.0 / 2025-09-06 22:10

## Governance_QA
Seq # (Chrono) | Phase | Sub-Process | Step Name | Detailed Instructions (Novice) | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | SLA Target (Response/Resolution/Due) | Inputs / Forms / Data | Outputs / Artifacts | SuiteDash Module / Feature | Automation Trigger (if any) | Automated Actions | Manual Actions | Dependencies (Predecessors) | Definition of Done (Checklist) | QA Gate / Approval | Exception Handling | Escalation Path | Metrics / KPI | Evidence Log / Where | Security / Data Class | Tools / Integrations | Template ID / Link (placeholder) | Owner (Role) | Version / Last Updated
1 | Governance & QA | Versioning | SOP Version Control & Change Log | Each SOP includes ID, version, owner, approver, change summary, next review date. Store in KB; restrict edit to owners. | Ops Manager | COO | Compliance | All Staff | Review cadence: annual (critical: semi-annual) | SOP templates; Change log | Updated SOP; Review task scheduled | Knowledge Base | New SOP uploaded/updated | Notify staff of changes | Update version; archive old | N/A | • Version header present • Next review set | COO approval | If conflicting SOPs → merge/retire | Escalate to COO | On-time reviews % | KB change log | Internal | None | SOP-HDR-001 | Ops Manager | v1.0 / 2025-09-06 22:10
2 | Governance & QA | QA | Monthly KPI & SLA Review | Run Ops review: SLA compliance, defects, rework, CSAT/NPS, utilization, margin. Log actions and owners. | Ops Manager | COO | PMs; CSM Lead; Support Lead | CEO | Meeting by 10th monthly | KPI dashboard; SLA report | Action log; Assigned tasks | Dashboards; Projects | Monthly schedule | Create 'Ops Improvements' project tasks | Host review; capture actions | N/A | • Actions assigned • Due dates set | COO sign-off | If chronic misses → capacity plan | Escalate to CEO if required | SLA met %, Defect trend | Meeting minutes | Internal | GA4/Stripe/etc. | MTG-OPS-REV | Ops Manager | v1.0 / 2025-09-06 22:10

## QA_Testing
Artifact Type | ID | Process / Area | Preconditions | Step-by-Step (Click Path) | Expected Result | Pass/Fail | Owner | Notes
EXPLANATION: Use these artifacts to ensure quality before and after changes. Start with UAT scripts to validate end-to-end flows, use regression checklists whenever you change forms/automations/templates, and follow the migration checklist to safely promote changes from sandbox to production.
UAT Script | UAT-ONB-001 | Onboarding → Kickoff | Test client exists; portal invite sent | 1) Login as client → 2) Open FLOW → 3) Complete Kickoff Form → 4) Book call → 5) Confirm email receipt | Client sees FLOW; form validates/mapping ok; meeting booked; confirmation emails/logs present |  | Ops QA
Regression Checklist | REG-FORM-001 | Forms & Mapping | Edited any Kickoff Form field/mapping | Re-submit test form; verify CRM mapping; verify automations fire; attachments saved; emails sent | All mappings correct; automations triggered; artifacts stored |  | Ops QA
Migration Checklist | MIG-001 | Sandbox → Production | Feature tested in sandbox; approvals in place | Export templates; backup current prod config; import; re-point IDs; run smoke tests; enable | Prod replicates sandbox results; no errors; rollback plan documented |  | Ops Admin

## Finance_SOPs
Process | Trigger/Event | Steps (Chronological) | SLA/Timing | Automation | Escalation | Controls (QA/Approval) | Evidence/Logs | Owner
EXPLANATION: Standardize money flows. Dunning = recover failed payments; refunds/chargebacks = protect CX and compliance; revenue recognition = record income correctly; reconciliation = keep Stripe/SuiteDash/Accounting in sync.
Dunning (Collections) | Invoice failed / subscription payment failed | Retry at T+0, T+3d, T+7d; send helpful emails; switch to manual invoice at T+10d; suspend service at T+14d (notify) | Email ≤1h; retries on schedule | AUTO dunning emails + status tags | Finance mgr at T+10d; Ops at T+14d | Refunds >$500 require approval; suspend checklist | Invoice status; email logs; tags | Finance
Refund / Chargeback | Client requests refund or bank chargeback | Validate eligibility; process partial/full; send confirmation; update subscription; document root cause | Acknowledge ≤1bd; resolve ≤5bd | Ticket → Finance task auto-created | Ops if disputes escalate | Manager approval for policy exceptions | Refund receipt; CRM note; ticket history | Finance
Revenue Recognition | Invoice issued/paid (project/recurring) | Mark revenue per schedule; defer unearned; allocate discounts; attach memos | Month-end | Accounting system rules | Finance Controller | PM review for milestones | Reports; journal entries | Finance
Reconciliation | Month-end close | Export Stripe; export SuiteDash; match payments/invoices; post adjustments; sign-off | By Day+5 | CSV exports + reconciliation sheet | Controller if variance >$100 | Two-person review | Recon worksheet; sign-off doc | Finance

## Security_Roles
Element | Item/Role | Definition / Scope | Access Level / Permission | Data Class (Public/Internal/Confidential/PII/PHI) | SOP / Link | Owner
EXPLANATION: Apply least-privilege access and compliance. Map roles to permissions, define data classes, document DSAR (GDPR) handling and breach response.
Role Matrix | Admin | Platform administrators (config & users) | Full admin; can edit templates and automations | All (including PII) | SOP-SEC-ROLES | IT/Security
Role Matrix | PM | Project managers | Projects/Tasks read-write; Billing read | Internal/Client docs | SOP-SEC-ROLES | Ops Manager
Role Matrix | CSM | Client success managers | Messages/Files read-write; CRM read-write | PII; Confidential | SOP-SEC-ROLES | CSM Lead
Role Matrix | Finance | Billing/accounting staff | Invoices/Subscriptions read-write | PII (billing) | SOP-SEC-ROLES | Finance Lead
Data Class | PII | Personally identifiable (emails, names, addresses) | Encrypted at rest; restricted export | PII | POL-DATA-CLASS | Compliance
Process | DSAR | Data subject access request handling | Verify identity; export data; deliver within statutory timeline | PII | SOP-DSAR | Compliance
Process | Breach Notification | Security incident affecting data | Severity assess; notify regulators/clients per law | PII/PHI | RUNBOOK-BREACH | IT/Security

## People_Training
Role | Training Module | Learning Objectives | Format | Duration | Assessment | Completion Criteria | Refresh Cadence | Backup/Shadow | Owner
EXPLANATION: Ensure every role can perform to standard. Use role-based curricula, certification checklists, refreshers, and backups for continuity.
PM | Onboarding SOP + FLOWs | Run kickoff; configure templates; set dependencies | SOP + Video + Shadow | 2h | Quiz (>=80%) | Shadow 1, lead 1 | Annual | PM2 | Ops Manager
CSM | Portal Orientation + Comms | Guide portal use; set expectations; manage updates | Video + Script + Roleplay | 1h | Roleplay scored | 1 successful orientation | Semiannual | CSM2 | CSM Lead
Support L1 | Tickets + SLA + Escalation | Categorize, triage, resolve/route within SLA | SOP + Lab | 3h | 3 mock tickets | Pass lab | Quarterly | L2 backup | Support Lead
Admin | Security & Automations | Maintain roles, logs, automations safely | Workshop + SOP | 2h | Change plan review | Promote 1 change w/o incident | Annual | Admin2 | IT/Security

## Continuity_Risk
Category | Scenario | Trigger | Immediate Actions (T+0-2h) | Stabilization (T+2-24h) | Recovery (≥24h) | Client Comms Template | Owner | Risk Level (L/M/H)
EXPLANATION: Plan for outages and high-risk events. Define failover steps, crisis communications, and track top risks with owners and mitigations.
Downtime | SuiteDash outage | Portal unreachable / status page red | Notify staff; switch to backup spreadsheets; pause automations | Process critical items manually; log work for later import | Bulk import records; reconcile tasks/data; RCA | Status note: outage acknowledged; ETA; workarounds provided | Ops Manager | H
Security | Credential leak | Suspicious access / alert | Rotate credentials; revoke tokens; force resets | Audit access; scan logs; notify stakeholders | RCA; update training; strengthen MFA | Incident notice: steps taken, impact, next actions | IT/Security | H
Vendor | Stripe API failure | Payments error spikes | Queue invoices; inform clients; retry later | Manual collection for critical items | Reconcile once vendor restored | Billing notice: payment processing delay, no action required | Finance | M

## Migration_Playbooks
Stage | Step # | Action | Owner | Tools/Links | Pass/Fail | Notes
EXPLANATION: Step-by-step to promote assets from sandbox to production and wire them in SuiteDash safely, with rollback.
Plan | 1 | List forms, templates, automations to change; capture IDs | Ops Admin | Asset inventory sheet
Plan | 2 | Define rollback for each asset (how to revert) | Ops Admin | Rollback doc
Build (Sandbox) | 3 | Clone & edit forms (fields/mapping/validation) | Ops Admin | SuiteDash Forms
Build (Sandbox) | 4 | Create/modify automations (triggers/actions) | Ops Admin | Automations
Test (Sandbox) | 5 | Run UAT scripts; fix defects; log results | Ops QA | QA_Testing sheet
Backup (Prod) | 6 | Export current prod templates/config; snapshot IDs | Ops Admin | Export/CSV
Promote (Prod) | 7 | Import/replicate assets; re-point IDs (forms, flows) | Ops Admin | SuiteDash
Smoke Test (Prod) | 8 | Run critical-path tests (new client → FLOW → project) | Ops QA | QA_Testing
Switch | 9 | Enable automations; disable legacy versions | Ops Admin | Automations
Monitor | 10 | Watch logs for 48h; rollback if severity ≥ Med | Ops Manager | Audit logs

## Industry_Healthcare_HIPAA
Domain | Element | Policy/Procedure | SuiteDash Implementation | Evidence/Logs | Owner
EXPLANATION: Healthcare variant: add HIPAA safeguards, BAAs, PHI handling, audit trails, and access restrictions for ePHI.
Access Control | Minimum Necessary | Limit PHI access to roles needing it | Circles/Teams: create PHI group; restrict file/folder access | Access review quarterly | Compliance
Agreements | BAA | Execute Business Associate Agreement with vendors | Store signed BAA in Legal archive; link to client | BAA repository | Legal
Security | Encryption | Encrypt PHI at rest/in transit | Ensure storage encryption; force HTTPS; avoid email attachments | Security config record | IT/Security
Privacy | Right of Access | Respond to patient DSAR in 30 days | DSAR SOP: export, redact, deliver via secure portal | DSAR ticket trail | Compliance
Incident | Breach Notification | Notify within 60 days; document | Runbook: severity assess, notify, RCA | Incident log | IT/Security

## Industry_Fintech_PCI
Domain | Element | Policy/Procedure | SuiteDash Implementation | Evidence/Logs | Owner
EXPLANATION: Fintech variant: payment security (PCI-DSS), anti-fraud, stronger authentication, and GDPR handling for EU clients.
Payment | PCI-DSS Scope | Do not store PAN; use Stripe vault only | Disable card storage in SuiteDash; Stripe hosted payment pages | Payment config audit | Finance/IT
Security | MFA | Mandatory MFA for admins & finance | Enforce MFA; document enrollment | MFA enrollment list | IT/Security
Privacy | GDPR DPA | Execute DPA, define SCCs if needed | Store signed DPA per client; tag EU accounts | DPA repo | Legal
Data | Retention | Minimize retention for PII | Auto-delete after 24 months inactivity | Retention job logs | Ops
Risk | Fraud Monitoring | Flag unusual billing patterns | Stripe Radar alerts → Support tickets | Alert history | Finance

## Sales_CLOSER_Automations
Stage | When Entering (Automations/Tasks) | Required Fields (Block Exit If Missing) | SLA / Timer | Exit Check (Definition of Done) | Escalation
EXPLANATION: Operational checklists for each CLOSER stage. Use this to wire 'Manage Automations' per stage and to define enforcement (required fields, tasks, emails) and SLAs.
Clarify | Assign SDR; start SOS sequence | Primary_Pain_Point | First touch ≤24h | Discovery booked OR clear disqualify | Sales Manager at +24h
Label | Create discovery task with script link | Problem_Label; Desired_Outcome | Discovery ≤3d | Discovery done (notes saved) | Sales Manager at +3d
Overview | Send demo prep email; calendar invite | Demo_Date; Stakeholders_Present | Demo ≤7d | Demo delivered | Sales Manager at +7d
Sell | Create proposal draft; internal pricing approval if needed | Objections_Raised; Responses_Given | Proposal ≤24h post-demo | Proposal sent | Ops for pricing exceptions
Explain | Schedule legal review; send FAQ/ROI one-pager | Decision_Factors | Follow-up every 48h | Verbal yes/contract redlines | Sales Manager if 0 activity 48h
Reinforce | Send social proof; confirm onboarding schedule | Close_Date | Close ≤14d | Signed + initial invoice paid | Escalate to AE Manager at +14d